## Sheet1
|  |  |  | Janith |  |  | Bhanuka |  |  | Dineth |  |  | Tharushan
Number |  |  | Description | Estimate | Actual | Mark | Estimate | Actual | Mark | Estimate | Actual | Mark | Estimate | Actual | Mark
Task 1 | Requirements Analyzing Phase 1 | 1 | Requirements Analyzing | 3 | 3 |  | 3 | 3 |  | 3 | 3 |  | 3 | 3
|  | 2 | Research about Similar Systems | 2 | 2 |  | 2 | 2 |  | 2 | 2 |  | 2 | 2
Task 2 | Client meetings | 1 | Cient Meeting 1 | 1 | 0 |  | 1 | 1 |  | 1 | 0 |  | 1 | 1
|  | 2 | Cient Meeting 2 | 1 | 1 |  | 1 | 0 |  | 1 | 1 |  | 1 | 0
|  | 3 | Cient Meeting 3 | 1 |  |  | 1 |  |  | 1 |  |  | 1
|  | 4 | Cient Meeting 4 | 1 |  |  | 1 |  |  | 1 |  |  | 1
|  | 5 | Cient Meeting 5 | 1 |  |  | 1 |  |  | 1 |  |  | 1
|  | 6 | Cient Meeting 6 | 1 |  |  | 1 |  |  | 1 |  |  | 1
|  | 7 | Cient Meeting 7 | 1 |  |  | 1 |  |  | 1 |  |  | 1
|  | 8 | Client Meeting Minutes 1 | [6 empty] | 1 | 1
|  | 9 | Client Meeting Minutes 2 | 1 | 1
|  | 10 | Client Meeting Minutes 3 |  |  |  | 1
|  | 11 | Client Meeting Minutes 4 | [6 empty] | 1
|  | 12 | Client Meeting Minutes 5 | [9 empty] | 1
|  | 13 | Client Meeting Minutes 6 | 1
|  | 14 | Client Meeting Minutes 7 |  |  |  | 1
Task 3 | Research the Software & Tools for the project | 1 | Find a suitable Database System |  |  |  | 2 | 2
|  | 2 | Find a Suitable Front End Framework | 2 | 2
|  | 3 | Research for the Tools | [9 empty] | 2 | 2
|  | 4 | find a suitable middle tier technologies | [6 empty] | 2 | 2
Task 4 | Preparing SRS Document | 1 | Prepare Introduction | 3 | 2
|  | 2 | Prepare Product Perspective and Fratures | 1 | 1
|  | 3 | Prepare "User Classes and Characteristics" and "Operating Environment" | [6 empty] | 1 | 0.75
|  | 4 | Prepare "Design and Implementation Constraints", "User Documentation" and "Assumptions and Dependencies" | [9 empty] | 2 | 2
|  | 5 | Prepare System Features (draft) | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  | 1 | 1
|  | 6 | Prepare Hardware Interface | [9 empty] | 1 | 1
|  | 7 | Prepare Software and Communications Interfaces |  |  |  | 1 | 1
|  | 8 | Prepare Other Nonfunctional Requirements |  |  |  | 2 | 2
|  | 9 | Prepare Appendix : Glossary | 0.5 | 0.5
|  | 10 | Prepare Appendix : Analysis Models | [6 empty] | 3.25 | 3
|  | 11 | Interfaces | 2 |  |  | 2 |  |  | 2 |  |  | 2
|  | 12 | ER Diagram | 2 | [5 empty] | 2
|  | 13 | Class Diagram |  |  |  | 2 | [5 empty] | 2
|  | 14 | System Features | 4 |  |  | 4 |  |  | 4 |  |  | 4
Task 5 | Learn MEAN Stack | 1 | Learn Angular | 4 | 3 |  | 4 |  |  | 4 | 4 |  | 4
|  | 2 | Learn Node and ExpressJS | 6 |  |  | 6 |  |  | 6 |  |  | 6
|  | 3 | Learn Mongo DB | 2 |  |  | 2 |  |  | 2 |  |  | 2
Task 6 | Setting Up the Development Environment | 1 | Setting up the individual development environment | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  | 1 | 1
|  | 2 | Setting up the repository and cloud tools | [9 empty] | 3 | 3
Task 7 | Sprint Plannings | 1 | Planning the user stories for the sprint 2 | 1 | 1 |  | 1 |  |  | 1 |  |  | 1
|  | 2 | Planning the user stories for the sprint 3 | 1 |  |  | 1 |  |  | 1 |  |  | 1
|  | 3 | Planning the user stories for the sprint 4 | 1 |  |  | 1 |  |  | 1 |  |  | 1
|  | 4 | Planning the user stories for the sprint 5 | 1 |  |  | 1 |  |  | 1 |  |  | 1
|  | 5 | Planning the user stories for the sprint 6 | 1 |  |  | 1 |  |  | 1 |  |  | 1
|  | 6 | Planning the user stories for the sprint 7 | 1 |  |  | 1 |  |  | 1 |  |  | 1
Task 8 | Sprint Retrospectives | 1 | Sprint 1 Retrospective | 0.5 | 0.5 |  | 0.5 |  |  | 0.5 | 0.5 |  | 0.5
|  | 2 | Sprint 2 Retrospective | 0.5 |  |  | 0.5 |  |  | 0.5 |  |  | 0.5
|  | 3 | Sprint 3 Retrospective | 0.5 |  |  | 0.5 |  |  | 0.5 |  |  | 0.5
|  | 4 | Sprint 4 Retrospective | 0.5 |  |  | 0.5 |  |  | 0.5 |  |  | 0.5
|  | 5 | Sprint 5 Retrospective | 0.5 |  |  | 0.5 |  |  | 0.5 |  |  | 0.5
|  | 6 | Sprint 6 Retrospective | 0.5 |  |  | 0.5 |  |  | 0.5 |  |  | 0.5
|  | 7 | Sprint 7 Retrospective | 0.5 |  |  | 0.5 |  |  | 0.5 |  |  | 0.5
Task 9 | Design Meetings | 1 | Discuss design issues | 5 |  |  | 5 |  |  | 5 |  |  | 5
Task 10 | Login | 1 | Login GUI | [6 empty] | 2
|  | 2 | Password Reset GUI | [6 empty] | 1
|  | 3 | Request for Forgot Password GUI | [6 empty] | 0.5
|  | 4 | Database Design | [6 empty] | 2
|  | 5 | Middle Tier Logic | [6 empty] | 2.5
|  | 6 | Presentation Tier Logic | [6 empty] | 7
|  | 7 | Testing | [6 empty] | 1
Task 11 | Homepage | 1 | Navigation Bar GUI | [6 empty] | 0.5
|  | 2 | Navigation Bar Routing | [6 empty] | 2
|  | 3 | Image Slider GUI | [6 empty] | 2
|  | 4 | Image Slider Implementation | [6 empty] | 3
|  | 5 | Database Design | [6 empty] | 0.5
|  | 6 | News Section Implementation | [6 empty] | 1
|  | 7 | Most Recent Project Section Implementation | [6 empty] | 1
|  | 8 | General Calendar GUI | [6 empty] | 2
|  | 9 | General Calendar Implementation | [6 empty] | 5
|  | 10 | Testing | [6 empty] | 1
Task 12 | General Photo Gallary Page | 1 | Main GUI Designing |  |  |  | 3
|  | 2 | Database Deigning |  |  |  | 1
|  | 3 | Presentation Tier Logic |  |  |  | 2
|  | 4 | Middle Tier Logic |  |  |  | 1
|  | 5 | Testing |  |  |  | 1
Task 13 | Admin Dashboard | 1 | Main GUI Draft Designing | 4
|  | 2 | Presentation Tier Logic | 3
|  | 3 | Database Design | 1
|  | 4 | Middle Tier Logic | 4
Task 14 | Membership Requests Page | 1 | All membership requests screen - GUI | 3
|  | 2 | All membership requests screen - Presentation Tier Logic | 2
|  | 3 | Detailed membership request screen - GUI | 3
|  | 4 | Detailed membership request screen - Implementation | 2
|  | 5 | All letters requests screen - GUI | 3
|  | 6 | All letters requests screen - Implementation | 2
|  | 7 | Detailed letter request screen - GUI | 3
|  | 8 | Detailed letter request screen - Implementation | 2
|  | 9 | Main GUI Finalized Design | 2
Task 15 | Project Planning Page | 1 | Create Project Page - Draft GUI | [9 empty] | 3
|  | 2 | Create Project Page - Database Design | [9 empty] | 1
|  | 3 | Create Project Page - Middle Tier Logic | [9 empty] | 2
|  | 4 | Create Project Page - Presentation Tier Logic | [9 empty] | 1
|  | 5 | View Project Page - Draft GUI | [9 empty] | 3
|  | 6 | Project Timeline - Draft GUI | [9 empty] | 3
|  | 7 | Project Timeline - Database Design | [9 empty] | 1
|  | 8 | Project Timeline - Middle Tier Logic | [9 empty] | 2
|  | 9 | Project Timeline - Presentation Tier Logic | [9 empty] | 2
|  | 10 | Project Timeline - Handling Photos and VIdeos | [9 empty] | 2
|  | 11 | Subscribe and Unsubscribe - Database Design | [9 empty] | 1
|  | 12 | Subscribe Project- Middle Tier Logic | [9 empty] | 2
|  | 13 | Subscribe Project - Presentation Tier Logic | [9 empty] | 1
|  | 14 | Unsubscribe Project - Middle Tier Logic | [9 empty] | 1
|  | 15 | Unsubscribe Project - Presentation Tier Logic | [9 empty] | 1
|  | 16 | View Subscribed Projects- Draft GUI | [9 empty] | 3
|  | 17 | View Update Feed for Subscribed Projects- Draft GUI | [9 empty] | 3
|  | 18 | View Update Feed for Subscribed Projects- Middle Tier Logic | [9 empty] | 2
|  | 19 | View Update Feed for Subscribed Projects- Presentation Tier Logic | [9 empty] | 1
|  | 20 | Suggestion and Complaint Page - Draft GUI | 3
|  | 21 | Suggestion and Complaint Page - Database Design | 1
|  | 22 | Suggestion and Complaint Page - Middle Tier Logic | 2
|  | 23 | Suggestion and Complaint Page - Presentation TIer Logic | 1
|  | 24 | Sub Projects - Database Design | [9 empty] | 1
|  | 25 | Sub Projects - Middle Tier Logic | [9 empty] | 2
|  | 26 | Sub Projects - Presentation Tier Logic | [9 empty] | 1
|  | 27 | Project Hierachichal View | [9 empty] | 4
|  | 28 | Testing | [9 empty] | 5
Task 16 | Account Handling | 1 | Create Account Page - Draft GUI |  |  |  | 3
|  | 2 | Create Account Page - Database Design |  |  |  | 1
|  | 3 | Create Account Page - Middle Tier Logic |  |  |  | 2
|  | 4 | Create Account Page - Presentation Tier Logic |  |  |  | 1
|  | 5 | View/Edit Account Page - Draft GUI |  |  |  | 3
|  | 6 | View/Edit Account Page - Middle Tier Logic |  |  |  | 2
|  | 7 | View/Edit Account Page - Presentation Tier Logic |  |  |  | 2
|  | 8 | Transaction Page - Draft GUI |  |  |  | 3
|  | 9 | Transaction Page - Middle Tier Logic |  |  |  | 2
|  | 10 | Transaction Page - Presentation Tier Logic |  |  |  | 1
|  | 11 | Account Summary Page - Draft GUI |  |  |  | 3
|  | 12 | Account Summary Page - Middle Tier Logic |  |  |  | 2
|  | 13 | Account Summary Page - Presentation Tier Logic |  |  |  | 1
|  | 14 | Testing |  |  |  | 5
Task 17 | Report Generation | 1 | Service letter generation GUI |  |  |  | 3
|  | 2 | Service letter generation Report |  |  |  | 2
|  | 3 | Contributions to the association GUI |  |  |  | 3
|  | 4 | Contributions to the association Report |  |  |  | 2
|  | 5 | Event Budget Details GUI |  |  |  | 3
|  | 6 | Project Budget Details Report |  |  |  | 2
|  | 7 | Project Committee Details GUI |  |  |  | 3
|  | 8 | Project Committee Details Report |  |  |  | 2
|  | 9 | Project Revenue and Profit Details GUI |  |  |  | 3
|  | 10 | Project Revenue and Profit Details Report |  |  |  | 2
|  | 11 | Periodic Reports for Accounts GUI |  |  |  | 3
|  | 12 | Periodic Reports for Accounts Report |  |  |  | 2
|  | 13 | Testing |  |  |  | 4
Task 18 | Members Dashboard | 1 | Letter Request - Draft GUI | [6 empty] | 3
|  | 2 | Letter Request - Database Design | [6 empty] | 1
|  | 3 | Letter Request - Middle Tier Logic | [6 empty] | 2
|  | 4 | Letter Request - Presentation Tier Logic | [6 empty] | 1
|  | 5 | Edit/ View Profile - Draft GUI | [6 empty] | 3
|  | 6 | Edit/ View Profile - Database Design | [6 empty] | 1
|  | 7 | Edit/ View Profile - Middle Tier Logic | [6 empty] | 2
|  | 8 | Edit/ View Profile - Presentation Tier Logic | [6 empty] | 1
|  | 9 | Membership Histroy - Draft GUI | [6 empty] | 3
|  | 10 | Membership Histroy - Database Design | [6 empty] | 1
|  | 11 | Membership Histroy - Middle Tier Logic | [6 empty] | 2
|  | 12 | Membership Histroy - Presentation Tier Logic | [6 empty] | 1
|  | 13 | Testing | [6 empty] | 4
Task 19 | System Log | 1 | System Log panal - Draft GUI | [9 empty] | 3
|  | 2 | Financial Transactions Section GUI - Draft GUI | [9 empty] | 2
|  | 3 | Detailed FInancial Transaction GUI - Draft GUI | [9 empty] | 3
|  | 4 | System Log panal - Database Design | [9 empty] | 1
|  | 5 | System Log panal - Middle Tier Logic | [9 empty] | 2
|  | 6 | System Log panal - Presentation Tier Logic | [9 empty] | 1
|  | 7 | Detailed Transaction Tier - Middle Tier Logic | [9 empty] | 2
|  | 8 | Detailed Transaction Screen - Presentation Tier Logic | [9 empty] | 1
|  | 9 | Testing | [9 empty] | 4
Task 20 | Acknowledgemt Mails | 1 | Acknowledgement Mails - Draft GUI | [9 empty] | 3
|  | 2 | Acknowledgement Mails - Database Design | [9 empty] | 1
|  | 3 | Acknowledgement Mails - Middle Tier Implementation | [9 empty] | 2
|  | 4 | Acknowledgement Mails - Presentation Tier Logic | [9 empty] | 1
|  | 5 | Testing | [9 empty] | 4
Task 21 | News Section Screen Edit (Admin) | 1 | News Section Screen GUI | 3
|  | 3 | Add/Edit News Items Presentation Tier Logic | 1
|  | 3 | Add/Edit News Items database design | 1
|  | 4 | Add/Edit News Items Middletier | 2
|  | 5 | Testing | 4
Task 22 | Executive Committee Management | 1 | Current ExCo Screen - Draft GUI | [6 empty] | 3
|  | 2 | Previous ExCos Screen - Draft GUI | [6 empty] | 3
|  | 3 | Detailed Exco Screen - Draft GUI | [6 empty] | 3
|  | 4 | Detailed Previous Exco Screen - Draft GUI | [6 empty] | 3
|  | 5 | ‌Add ExCo members and map user roles Screen - Draft GUI | [6 empty] | 3
|  | 6 | Add Exco Members - Presentation Tier Logic | [6 empty] | 1
|  | 7 | Add Exco Members - Middle Tier Logic | [6 empty] | 2
|  | 8 | Testing | [6 empty] | 4
Task 23 | Online Payment Gateway | 1 | Research for a suitable online payment gateway | 5
|  | 2 | Setup the payment gateway | 2
|  | 3 | Payment Page - Draft GUI | 3
|  | 4 | Payment Page - Database Design | 2
|  | 5 | Payment Page - Middle Tier Logic | 2
|  | 6 | Payment Page - Presentation Tier Logic | 1
|  | 7 | Testing | 5
Task 24 |  | 1 | Member Directory Draft GUI |  |  |  | 3
|  | 2 | Member Directory Middle Tier |  |  |  | 2
|  | 3 | Member Directory Presentation Tier |  |  |  | 2
|  | 4 | Member Detail View GUI |  |  |  | 3
|  | 5 | Member Detail View Middle Tier |  |  |  | 2
|  | 6 | Member Detail View Presentation Tier |  |  |  | 1
Task 25 | Preparation of Task Allocation | 1 | Planning the Task Allocation | 3 | 3 |  | 3 |  |  | 3 |  |  | 3
|  | 2 | Documenting the Task Breakdowns | 5 | 5 |  | 5 |  |  | 5 |  |  | 5
Task 26 | System Test | 1 | Full flow Testing | 4 |  |  | 1 |  |  | 1 |  |  | 2
|  | 2 | Bug Fixing | 4 |  |  | 1 |  |  | 1 |  |  | 2
Task 27 | Documentation | 1 | User Guide | 2 |  |  | 2 |  |  | 2 |  |  | 2
Total |  |  |  | 147 |  |  | 153.5 |  |  | 149.75 |  |  | 149.5