## Sheet1
|  |  |  | Janith |  |  | Bhanuka |  |  | Dineth |  |  | Tharushan
Number |  |  | Description | Estimate | Actual | Mark | Estimate | Actual | Mark | Estimate | Actual | Mark | Estimate | Actual | Mark
Task 1 | Requirements Analyzing Phase 1 | 1 | Requirements Analyzing | 3 | 3 |  | 3 | 3 |  | 3 | 3 |  | 3 | 3
|  | 2 | Research about Similar Systems | 2 | 2 |  | 2 | 2 |  | 2 | 2 |  | 2 | 2
Task 2 | Research the Software & Tools for the project | 1 | Find a suitable Database System |  |  |  | 2 | 2
|  | 2 | Find a Suitable Front End Framework | 2 | 2
|  | 3 | Research for the Tools | [9 empty] | 2 | 2
|  | 4 | find a suitable middle tier technologies | [6 empty] | 2 | 2
Task 3 | Preparing SRS Document | 1 | Prepare Introduction | 3 | 2
|  | 2 | Prepare Product Perspective and Fratures | 1 | 1
|  | 3 | Prepare "User Classes and Characteristics" and "Operating Environment" | [6 empty] | 1 | 0.75
|  | 4 | Prepare "Design and Implementation Constraints", "User Documentation" and "Assumptions and Dependencies" | [9 empty] | 2 | 2
|  | 5 | Prepare System Features (draft) | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  | 1 | 1
|  | 6 | Prepare Hardware Interface | [9 empty] | 1 | 1
|  | 7 | Prepare Software and Communications Interfaces |  |  |  | 1 | 1
|  | 8 | Prepare Other Nonfunctional Requirements |  |  |  | 2 | 2
|  | 9 | Prepare Appendix : Glossary | 0.5 | 0.5
|  | 10 | Prepare Appendix : Analysis Models | [6 empty] | 3.25 | 3
|  | 11 | Interfaces | 2 |  |  | 2 |  |  | 2 |  |  | 2
|  | 12 | ER Diagram | 2 | [5 empty] | 2
|  | 13 | Class Diagram |  |  |  | 2 | [5 empty] | 2
|  | 14 | System Features | 4 |  |  | 4 |  |  | 4 |  |  | 4
Task 4 | Learn MEAN Stack | 1 | Learn Angular | 4 | 3 |  | 4 |  |  | 4 | 4 |  | 4
|  | 2 | Learn Node and ExpressJS | 6 |  |  | 6 |  |  | 6 |  |  | 6
|  | 3 | Learn Mongo DB | 2 |  |  | 2 |  |  | 2 |  |  | 2
Task 5 | Setting Up the Development Environment | 1 | Setting up the individual development environment | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  | 1 | 1
|  | 2 | Setting up the repository and cloud tools | [9 empty] | 3 | 3
Task 6 | Sprint Plannings | 1 | Planning the user stories for the sprint 2 | 1 | 1 |  | 1 |  |  | 1 |  |  | 1
|  | 2 | Planning the user stories for the sprint 3 | 1 | 1 |  | 1 |  |  | 1 |  |  | 1
|  | 3 | Planning the user stories for the sprint 4 | 1 | 1 |  | 1 |  |  | 1 |  |  | 1
|  | 4 | Planning the user stories for the sprint 5 | 1 |  |  | 1 |  |  | 1 |  |  | 1
|  | 5 | Planning the user stories for the sprint 6 | 1 |  |  | 1 |  |  | 1 |  |  | 1
|  | 6 | Planning the user stories for the sprint 7 | 1 |  |  | 1 |  |  | 1 |  |  | 1
Task 7 | Sprint Retrospectives | 1 | Sprint 1 Retrospective | 0.5 | 0.5 |  | 0.5 |  |  | 0.5 | 0.5 |  | 0.5
|  | 2 | Sprint 2 Retrospective | 0.5 | 0.5 |  | 0.5 |  |  | 0.5 |  |  | 0.5
|  | 3 | Sprint 3 Retrospective | 0.5 | 0.5 |  | 0.5 |  |  | 0.5 |  |  | 0.5
|  | 4 | Sprint 4 Retrospective | 0.5 |  |  | 0.5 |  |  | 0.5 |  |  | 0.5
|  | 5 | Sprint 5 Retrospective | 0.5 |  |  | 0.5 |  |  | 0.5 |  |  | 0.5
|  | 6 | Sprint 6 Retrospective | 0.5 |  |  | 0.5 |  |  | 0.5 |  |  | 0.5
|  | 7 | Sprint 7 Retrospective | 0.5 |  |  | 0.5 |  |  | 0.5 |  |  | 0.5
Task 8 | Design Meetings | 1 | Discuss design issues | 8 |  |  | 8 |  |  | 8 |  |  | 8
Task 9 | Intial Project Creation | 1 | Implement Build Tools - Heroku | [9 empty] | 1
|  | 2 | Implement Hosting Environment - Heroku | [9 empty] | 2
|  | 3 | Create Initial Project Structure | [9 empty] | 2
|  | 4 | Create MongoDB database on MongoDB Atlas | [9 empty] | 1
|  | 5 | Create Express server and Implement DB Connection | [9 empty] | 2
Task 10 | Login Page Designing | 1 | Login GUI Design | [6 empty] | 1
|  | 2 | Login GUI Implemantation | [6 empty] | 2
|  | 3 | Password Reset Implementation | [6 empty] | 2
|  | 4 | Request for Forgot Password GUI Design | [6 empty] | 1
|  | 5 | Request for Forgot Password Implementation | [6 empty] | 2
|  | 6 | Login Insert Method | [6 empty] | 2
|  | 7 | Get Login details Method | [6 empty] | 2
|  | 8 | Login Update Method | [6 empty] | 2
|  | 9 | Login Delete Method | [6 empty] | 2
|  | 10 | Database Design | [6 empty] | 1
|  | 11 | Login User Validation | [6 empty] | 2
|  | 12 | E-mail sending Implementation | [6 empty] | 3
Task 11 | Homepage Designing | 1 | Homepage GUI Design | [6 empty] | 2
|  | 2 | Navigation Bar GUI Implementation | [6 empty] | 2
|  | 3 | Navigation Bar Routing Implementation | [6 empty] | 1
|  | 4 | Image Slider GUI | [6 empty] | 2
|  | 5 | Image Slider Implementation | [6 empty] | 3
|  | 6 | Database Design | [6 empty] | 1
|  | 7 | News Section Implementation | [6 empty] | 2
|  | 8 | Most Recent Project Section Implementation | [6 empty] | 2
|  | 9 | General Calendar GUI Design | [6 empty] | 2
|  | 10 | General Calendar Implementation | [6 empty] | 5
Task 12 | General Photo Gallary Page | 1 | Gallery Page Main GUI Designing |  |  |  | 1
|  | 2 | Gallery Page Main GUI Implementation |  |  |  | 3
|  | 3 | Database Deigning |  |  |  | 1
|  | 4 | Gallery Page Insert Methods |  |  |  | 2
|  | 5 | Gallery Page Delete Methods |  |  |  | 2
|  | 6 | Gallery Page Validations |  |  |  | 2
Task 13 | Admin Dashboard Designing | 1 | Main GUI Designing | 2 | 1
|  | 2 | Main GUI Implementation | 3 | 4
|  | 3 | Summay View Methods | 3
Task 14 | Request New Membership Page Implementation | 1 | New Membership Page Designing | 2 | 2
|  | 2 | New Membership GUI Implementation | 12 | 13
|  | 3 | New Membership Page Validation Methods | 2 | 3
|  | 4 | Membership Database Design | 1 | 1
|  | 5 | New Membership Page CRUD operations | 6 | 5
Task 15 | Review Membership Requests Page Designing (Admin) | 1 | All membership requests screen Design | 1
|  | 2 | All membership requests screen Implementation | 3
|  | 3 | Membership Requests Accept Functionality | 1
|  | 4 | Membership Requests Reject Functionality | 1
|  | 5 | All membership Requests Validation Methods | 1
|  | 6 | Detailed membership Request screen GUI Implementation | 3
Task 16 | Review Letter Requests Page Implemantation (Admin) | 1 | All Letters Requests GUI Designing & Implementation | 3
|  | 2 | All Letter Requests Screen Filtering Methods | 3
|  | 3 | Detailed Letter Request Screen GUI Designing | 2
|  | 4 | Detailed Letter Request Screen GUI Implementation | 3
|  | 5 | Letter Request Screen Accept Functionality | 2
|  | 6 | Letter Request Screen Reject Functionality | 2
|  | 7 | Letter Preparation GUI Designing | 1
|  | 8 | Letter Preparation GUI Implementation | 2
|  | 9 | PDF Creation Functionality | 3
|  | 10 | Letter Requests Insert Methods | 1
|  | 11 | Letter Requests Get Methods | 1
|  | 12 | Letter Requests Update Methods | 1
|  | 13 | Letter Requests Delete Methods | 1
Task 17 | Project Planning Page Designing | 1 | Detailed Project Page - GUI Designing | [9 empty] | 1
|  | 2 | Detailed Project Page - GUI Implementation | [9 empty] | 3
|  | 3 | Detailed Project Page - Validation Methods | [9 empty] | 2
|  | 4 | Detailed Project Page - Database Designing | [9 empty] | 1
|  | 5 | Detailed Project Page - Insert Methods | [9 empty] | 2
|  | 6 | Detailed Project Page - Update Methods | [9 empty] | 2
|  | 7 | Detailed Project Page - Delete Methods | [9 empty] | 2
|  | 8 | Project List Page - GUI Designing & Implementation | [9 empty] | 3.5
|  | 9 | Project List Page - Search Methods | [9 empty] | 2
|  | 10 | Project Timeline - GUI Designing | [9 empty] | 1
|  | 11 | Project Timeline - GUI Implementation | [9 empty] | 3
|  | 12 | Project Timeline - Validation Methods | [9 empty] | 2
|  | 13 | Project Timeline - Database Design | [9 empty] | 1
|  | 14 | Project Timeline - Insert Methods | [9 empty] | 2
|  | 15 | Project Timeline - Update Methods | [9 empty] | 2
|  | 16 | Project Timeline - Delete Methods | [9 empty] | 2
|  | 17 | Project Subscription - Database Design | [9 empty] | 1
|  | 18 | Project Subscription - Insert Methods | [9 empty] | 2
|  | 19 | Project Subscription - Update Methods | [9 empty] | 2
|  | 20 | Project Subscription - Delete Methods | [9 empty] | 2
|  | 21 | Project Subscription - Validation Methods | [9 empty] | 1
|  | 22 | Project Subscription List - GUI Designing and Implementation | [9 empty] | 3.5
|  | 23 | Update Feed for Subscribed Projects- GUI Designing and Implementation | [9 empty] | 3
|  | 24 | Suggestion and Complaint Page - GUI Design | 2
|  | 25 | Suggestion and Complaint Page - GUI Implementation | 3
|  | 26 | Suggestion and Complaint Page - Validation Methods | 2
|  | 27 | Suggestion and Complaint Page - Insert Methods | 2
|  | 28 | Suggestion and Complaint Page - Update Methods | 2
|  | 29 | Suggestion and Complaint Page - Delete Methods | 2
|  | 30 | Sub Projects - Database Design | [9 empty] | 1
|  | 31 | Sub Projects - Insert Methods | [9 empty] | 2
|  | 32 | Sub Projects - Update Methods | [9 empty] | 2
|  | 33 | Sub Projects - Delete Methods | [9 empty] | 2
|  | 34 | Sub Projects - GUI Designing | [9 empty] | 1
|  | 35 | Sub Projects - GUI Implementation | [9 empty] | 3
Task 18 | Account Handling Development | 1 | Main Accounts Page Designing & Implementation |  |  |  | 3
|  | 2 | All Accounts Page Designing & Implementation |  |  |  | 2
|  | 3 | Detailed Account Page Designing |  |  |  | 1
|  | 4 | Detailed Account Page Implementation |  |  |  | 4
|  | 5 | Detailed Account Page - Database Design |  |  |  | 1
|  | 6 | Detailed Account Page - Insert Method Calls |  |  |  | 2
|  | 7 | Detailed Account Page Update Method Calls |  |  |  | 2
|  | 8 | Detailed Account Page Delete Method Calls |  |  |  | 2
|  | 9 | Detailed Account Page Search & Filtering Method Calls |  |  |  | 4
|  | 10 | Detailed Account Page Validation Methods |  |  |  | 2
|  | 11 | Detailed Account Page Transaction Table Insert Methods |  |  |  | 2
|  | 12 | Detailed Account Page Transaction Table Update Methods |  |  |  | 3
|  | 13 | Detailed Account Page Transaction Table Delete Methods |  |  |  | 2
|  | 14 | Detailed Account Page Transaction Table Search Methods |  |  |  | 1
|  | 15 | Account Report Page GUI Designing |  |  |  | 2
|  | 16 | Account Report Page GUI Implementation |  |  |  | 3
|  | 17 | Account Report Page GUI Report Generation Algorithm |  |  |  | 4
Task 19 | Report Generation Implemantation | 1 | Service Letter Generation GUI Designing & Implementation |  |  |  | 3
|  | 2 | Service letter generation Report Designing |  |  |  | 2
|  | 3 | Contributions to the association GUI Designing & Implementation |  |  |  | 3
|  | 4 | Contributions to the association Report Designing |  |  |  | 2
|  | 5 | Event Budget Details GUI Designing & Implementation |  |  |  | 3
|  | 6 | Project Budget Details Report Designing |  |  |  | 2
|  | 7 | Project Committee Details GUI Designing & Implementation |  |  |  | 3
|  | 8 | Project Committee Details Report Designing |  |  |  | 2
|  | 9 | Project Revenue and Profit Details GUI Designing & Implementation |  |  |  | 3
|  | 10 | Project Revenue and Profit Details Report Designing |  |  |  | 2
|  | 11 | Periodic Reports for Accounts GUI Designing & Implementation |  |  |  | 3
|  | 12 | Periodic Reports for Accounts Report Designing |  |  |  | 2
Task 20 | Official Letter Requesting Page Implementation | 1 | Letter Request - GUI Designing | [6 empty] | 1
|  | 2 | Letter Request - GUI Implemantation | [6 empty] | 2
|  | 3 | Letter Request - Database Design | [6 empty] | 1
|  | 4 | Letter Request Validation Methods | [6 empty] | 1
|  | 5 | Letter Request Insert Methods | [6 empty] | 2
|  | 6 | Letter Request Update Methods | [6 empty] | 2
|  | 7 | Letter Request Read Methods | [6 empty] | 2
|  | 8 | Letter Request Delete Methods | [6 empty] | 2
Task 21 | Implemetation of Member Profile Page | 1 | Detailed Profile GUI Designing | [6 empty] | 1
|  | 2 | Detailed Profile GUI Implemantation | [6 empty] | 3
|  | 3 | Detailed Profile Database Design | [6 empty] | 2
|  | 4 | Detailed Profile Validation Methods | [6 empty] | 2
|  | 6 | Detailed Profile Update Methods | [6 empty] | 2
|  | 7 | Detailed Profile Delete Methods | [6 empty] | 2
Task 22 | Members Dashboard Designing | 1 | Member Dashboard - GUI Designing | [6 empty] | 1
|  | 2 | Member Dashboard - GUI Implementation | [6 empty] | 3
|  | 3 | Member Dashboard - Summary View Methods | [6 empty] | 3
Task 23 | Membership History Page Implementation | 1 | Membership Histroy - GUI Design | [9 empty] | 3
|  | 2 | Membership Histroy - GUI Implemantation | [9 empty] | 3
|  | 3 | Membership Histroy - Database Design | [9 empty] | 2
|  | 4 | Membership Histroy Search & filtering | [9 empty] | 2
Task 24 | System Log Development | 1 | System Log panal - GUI Design | [9 empty] | 1
|  | 2 | System Log Panel GUI Implementation | [9 empty] | 3
|  | 3 | Detailed FInancial Transaction GUI Design | [9 empty] | 1
|  | 4 | Detailed FInancial Transaction GUI Implementation | [9 empty] | 2
|  | 5 | System Log panel - Database Design | [9 empty] | 2
|  | 6 | System Log panel Search & Filter Methods | [9 empty] | 3
|  | 7 | Transaction Log Search & Filter Methods | [9 empty] | 2
|  | 8 | Detailed Transaction Read Methods | [9 empty] | 2
Task 25 | Acknowledgemt Mails Implemantation | 1 | Acknowledgement Mails - GUI Design and Implemetation | [9 empty] | 3
|  | 2 | Acknowledgement Mails - Logic Implemetaion | [9 empty] | 1
Task 26 | Edit News Implementation (Admin) | 1 | News Screen GUI Design | 1 | 1
|  | 2 | News Screen GUI Implementation | 3 | 4
|  | 3 | News Screen Database Design | 1 | 1
|  | 4 | News Screen Validation Methods | 2 | 3
|  | 5 | News Screen Insert Methods | 2 | 1
|  | 6 | News Screen Update Methods | 2 | 2
|  | 7 | News Screen Delete Methods | 2 | 2
Task 27 | Executive Committee Management Page Designing | 1 | Current ExCo Screen - GUI Design | [6 empty] | 1
|  | 2 | Current ExCo Screen - GUI Implemantation | [6 empty] | 3
|  | 3 | Previous ExCos Screen - GUI Design | [6 empty] | 2
|  | 4 | Previous ExCos Screen - GUI Implemantation | [6 empty] | 3
|  | 5 | Detailed Exco Screen - GUI Design | [6 empty] | 2
|  | 6 | Detailed Exco Screen - GUI Implemantation | [6 empty] | 3
|  | 7 | Detailed Previous Exco Screen - GUI Design | [6 empty] | 2
|  | 8 | Detailed Previous Exco Screen - GUI Implemantation | [6 empty] | 3
|  | 9 | ‌Add ExCo members and map user roles Screen - GUI Design | [6 empty] | 1
|  | 10 | ‌Add ExCo members and map user roles Screen - GUI Implemantation | [6 empty] | 2
|  | 11 | Add Exco Members Insert Methods | [6 empty] | 2
|  | 12 | Add Exco Members Update Methods | [6 empty] | 2
|  | 13 | Add Exco Members Delete Methods | [6 empty] | 2
|  | 14 | Add Exco Members Validation | [6 empty] | 2
Task 28 | Online Payment Gateway Development | 1 | Research for a suitable online payment gateway | 5
|  | 2 | Setup the payment gateway | 2
|  | 3 | Payment Page GUI Designing | 2
|  | 4 | Payment Page GUI Implementation | 3
|  | 5 | Payment Page - Database Design | 2
|  | 6 | Payment Page Validation Methods | 2
|  | 7 | Payment Page Insert Methods | 2
|  | 8 | Payment Page Update Methods | 3
Task 29 | Member Directory Implementation | 1 | Member Directory GUI Design |  |  |  | 3
|  | 2 | Member Directory GUI Implementation |  |  |  | 2
|  | 3 | Member Directory GUI Validations |  |  |  | 2
|  | 4 | Member Detail View GUI Implementation |  |  |  | 3
|  | 5 | Member Detail Update Implementation |  |  |  | 2
|  | 6 | Member Details Delete Implementation |  |  |  | 2
|  | 7 | Member Details Search Functionality with Filtering Implementation |  |  |  | 4
Task 30 | Preparation of Task Allocation | 1 | Planning the Task Allocation | 3 | 3 |  | 3 |  |  | 3 |  |  | 3
|  | 2 | Documenting the Task Breakdowns | 5 | 5 |  | 5 |  |  | 5 |  |  | 5
Task 31 | System Test | 1 | Full flow Testing | 4 |  |  | 2 |  |  | 2 |  |  | 2
|  | 2 | Bug Fixing | 4 |  |  | 4 |  |  | 4 |  |  | 4
Task 32 | Documentation | 1 | User Guide | 2 |  |  | 2 |  |  | 2 |  |  | 2
Total |  |  |  | 182 |  |  | 164.5 |  |  | 172.75 |  |  | 163.5

## Original
|  |  |  | Janith |  |  | Bhanuka |  |  | Dineth |  |  | Tharushan
Number |  |  | Description | Estimate | Actual | Mark | Estimate | Actual | Mark | Estimate | Actual | Mark | Estimate | Actual | Mark
Task 1 | Requirements Analyzing Phase 1 | 1 | Requirements Analyzing | 3 | 3 |  | 3 | 3 |  | 3 | 3 |  | 3 | 3
|  | 2 | Research about Similar Systems | 2 | 2 |  | 2 | 2 |  | 2 | 2 |  | 2 | 2
Task 3 | Research the Software & Tools for the project | 1 | Find a suitable Database System |  |  |  | 2 | 2
|  | 2 | Find a Suitable Front End Framework | 2 | 2
|  | 3 | Research for the Tools | [9 empty] | 2 | 2
|  | 4 | find a suitable middle tier technologies | [6 empty] | 2 | 2
Task 4 | Preparing SRS Document | 1 | Prepare Introduction | 3 | 2
|  | 2 | Prepare Product Perspective and Fratures | 1 | 1
|  | 3 | Prepare "User Classes and Characteristics" and "Operating Environment" | [6 empty] | 1 | 0.75
|  | 4 | Prepare "Design and Implementation Constraints", "User Documentation" and "Assumptions and Dependencies" | [9 empty] | 2 | 2
|  | 5 | Prepare System Features (draft) | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  | 1 | 1
|  | 6 | Prepare Hardware Interface | [9 empty] | 1 | 1
|  | 7 | Prepare Software and Communications Interfaces |  |  |  | 1 | 1
|  | 8 | Prepare Other Nonfunctional Requirements |  |  |  | 2 | 2
|  | 9 | Prepare Appendix : Glossary | 0.5 | 0.5
|  | 10 | Prepare Appendix : Analysis Models | [6 empty] | 3.25 | 3
|  | 11 | Interfaces | 2 |  |  | 2 |  |  | 2 |  |  | 2
|  | 12 | ER Diagram | 2 | [5 empty] | 2
|  | 13 | Class Diagram |  |  |  | 2 | [5 empty] | 2
|  | 14 | System Features | 4 |  |  | 4 |  |  | 4 |  |  | 4
Task 5 | Learn MEAN Stack | 1 | Learn Angular | 4 | 3 |  | 4 |  |  | 4 | 4 |  | 4
|  | 2 | Learn Node and ExpressJS | 6 |  |  | 6 |  |  | 6 |  |  | 6
|  | 3 | Learn Mongo DB | 2 |  |  | 2 |  |  | 2 |  |  | 2
Task 6 | Setting Up the Development Environment | 1 | Setting up the individual development environment | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  | 1 | 1
|  | 2 | Setting up the repository and cloud tools | [9 empty] | 3 | 3
Task 7 | Sprint Plannings | 1 | Planning the user stories for the sprint 2 | 1 | 1 |  | 1 |  |  | 1 |  |  | 1
|  | 2 | Planning the user stories for the sprint 3 | 1 |  |  | 1 |  |  | 1 |  |  | 1
|  | 3 | Planning the user stories for the sprint 4 | 1 |  |  | 1 |  |  | 1 |  |  | 1
|  | 4 | Planning the user stories for the sprint 5 | 1 |  |  | 1 |  |  | 1 |  |  | 1
|  | 5 | Planning the user stories for the sprint 6 | 1 |  |  | 1 |  |  | 1 |  |  | 1
|  | 6 | Planning the user stories for the sprint 7 | 1 |  |  | 1 |  |  | 1 |  |  | 1
Task 8 | Sprint Retrospectives | 1 | Sprint 1 Retrospective | 0.5 | 0.5 |  | 0.5 |  |  | 0.5 | 0.5 |  | 0.5
|  | 2 | Sprint 2 Retrospective | 0.5 |  |  | 0.5 |  |  | 0.5 |  |  | 0.5
|  | 3 | Sprint 3 Retrospective | 0.5 |  |  | 0.5 |  |  | 0.5 |  |  | 0.5
|  | 4 | Sprint 4 Retrospective | 0.5 |  |  | 0.5 |  |  | 0.5 |  |  | 0.5
|  | 5 | Sprint 5 Retrospective | 0.5 |  |  | 0.5 |  |  | 0.5 |  |  | 0.5
|  | 6 | Sprint 6 Retrospective | 0.5 |  |  | 0.5 |  |  | 0.5 |  |  | 0.5
|  | 7 | Sprint 7 Retrospective | 0.5 |  |  | 0.5 |  |  | 0.5 |  |  | 0.5
Task 9 | Design Meetings | 1 | Discuss design issues | 5 |  |  | 5 |  |  | 5 |  |  | 5
Task 10 | Login | 1 | Login GUI | [6 empty] | 2
|  | 2 | Password Reset GUI | [6 empty] | 1
|  | 3 | Request for Forgot Password GUI | [6 empty] | 0.5
|  | 4 | Database Design | [6 empty] | 2
|  | 5 | Middle Tier Logic | [6 empty] | 2.5
|  | 6 | Presentation Tier Logic | [6 empty] | 7
|  | 7 | Testing | [6 empty] | 1
Task 11 | Homepage | 1 | Navigation Bar GUI | [6 empty] | 0.5
|  | 2 | Navigation Bar Routing | [6 empty] | 2
|  | 3 | Image Slider GUI | [6 empty] | 2
|  | 4 | Image Slider Implementation | [6 empty] | 3
|  | 5 | Database Design | [6 empty] | 0.5
|  | 6 | News Section Implementation | [6 empty] | 1
|  | 7 | Most Recent Project Section Implementation | [6 empty] | 1
|  | 8 | General Calendar GUI | [6 empty] | 2
|  | 9 | General Calendar Implementation | [6 empty] | 5
|  | 10 | Testing | [6 empty] | 1
Task 12 | General Photo Gallary Page | 1 | Main GUI Designing |  |  |  | 3
|  | 2 | Database Deigning |  |  |  | 1
|  | 3 | Presentation Tier Logic |  |  |  | 2
|  | 4 | Middle Tier Logic |  |  |  | 1
|  | 5 | Testing |  |  |  | 1
Task 13 | Admin Dashboard | 1 | Main GUI Draft Designing | 4
|  | 2 | Presentation Tier Logic | 3
|  | 3 | Database Design | 1
|  | 4 | Middle Tier Logic | 4
Task 14 | Membership Requests Page | 1 | All membership requests screen - GUI | 3
|  | 2 | All membership requests screen - Presentation Tier Logic | 2
|  | 3 | Detailed membership request screen - GUI | 3
|  | 4 | Detailed membership request screen - Implementation | 2
|  | 5 | All letters requests screen - GUI | 3
|  | 6 | All letters requests screen - Implementation | 2
|  | 7 | Detailed letter request screen - GUI | 3
|  | 8 | Detailed letter request screen - Implementation | 2
|  | 9 | Main GUI Finalized Design | 2
Task 15 | Project Planning Page | 1 | Create Project Page - Draft GUI | [9 empty] | 3
|  | 2 | Create Project Page - Database Design | [9 empty] | 1
|  | 3 | Create Project Page - Middle Tier Logic | [9 empty] | 2
|  | 4 | Create Project Page - Presentation Tier Logic | [9 empty] | 1
|  | 5 | View Project Page - Draft GUI | [9 empty] | 3
|  | 6 | Project Timeline - Draft GUI | [9 empty] | 3
|  | 7 | Project Timeline - Database Design | [9 empty] | 1
|  | 8 | Project Timeline - Middle Tier Logic | [9 empty] | 2
|  | 9 | Project Timeline - Presentation Tier Logic | [9 empty] | 2
|  | 10 | Project Timeline - Handling Photos and VIdeos | [9 empty] | 2
|  | 11 | Subscribe and Unsubscribe - Database Design | [9 empty] | 1
|  | 12 | Subscribe Project- Middle Tier Logic | [9 empty] | 2
|  | 13 | Subscribe Project - Presentation Tier Logic | [9 empty] | 1
|  | 14 | Unsubscribe Project - Middle Tier Logic | [9 empty] | 1
|  | 15 | Unsubscribe Project - Presentation Tier Logic | [9 empty] | 1
|  | 16 | View Subscribed Projects- Draft GUI | [9 empty] | 3
|  | 17 | View Update Feed for Subscribed Projects- Draft GUI | [9 empty] | 3
|  | 18 | View Update Feed for Subscribed Projects- Middle Tier Logic | [9 empty] | 2
|  | 19 | View Update Feed for Subscribed Projects- Presentation Tier Logic | [9 empty] | 1
|  | 20 | Suggestion and Complaint Page - Draft GUI | 3
|  | 21 | Suggestion and Complaint Page - Database Design | 1
|  | 22 | Suggestion and Complaint Page - Middle Tier Logic | 2
|  | 23 | Suggestion and Complaint Page - Presentation TIer Logic | 1
|  | 24 | Sub Projects - Database Design | [9 empty] | 1
|  | 25 | Sub Projects - Middle Tier Logic | [9 empty] | 2
|  | 26 | Sub Projects - Presentation Tier Logic | [9 empty] | 1
|  | 27 | Project Hierachichal View | [9 empty] | 4
|  | 28 | Testing | [9 empty] | 5
Task 16 | Account Handling | 1 | Create Account Page - Draft GUI |  |  |  | 3
|  | 2 | Create Account Page - Database Design |  |  |  | 1
|  | 3 | Create Account Page - Middle Tier Logic |  |  |  | 2
|  | 4 | Create Account Page - Presentation Tier Logic |  |  |  | 1
|  | 5 | View/Edit Account Page - Draft GUI |  |  |  | 3
|  | 6 | View/Edit Account Page - Middle Tier Logic |  |  |  | 2
|  | 7 | View/Edit Account Page - Presentation Tier Logic |  |  |  | 2
|  | 8 | Transaction Page - Draft GUI |  |  |  | 3
|  | 9 | Transaction Page - Middle Tier Logic |  |  |  | 2
|  | 10 | Transaction Page - Presentation Tier Logic |  |  |  | 1
|  | 11 | Account Summary Page - Draft GUI |  |  |  | 3
|  | 12 | Account Summary Page - Middle Tier Logic |  |  |  | 2
|  | 13 | Account Summary Page - Presentation Tier Logic |  |  |  | 1
|  | 14 | Testing |  |  |  | 5
Task 17 | Report Generation | 1 | Service letter generation GUI |  |  |  | 3
|  | 2 | Service letter generation Report |  |  |  | 2
|  | 3 | Contributions to the association GUI |  |  |  | 3
|  | 4 | Contributions to the association Report |  |  |  | 2
|  | 5 | Event Budget Details GUI |  |  |  | 3
|  | 6 | Project Budget Details Report |  |  |  | 2
|  | 7 | Project Committee Details GUI |  |  |  | 3
|  | 8 | Project Committee Details Report |  |  |  | 2
|  | 9 | Project Revenue and Profit Details GUI |  |  |  | 3
|  | 10 | Project Revenue and Profit Details Report |  |  |  | 2
|  | 11 | Periodic Reports for Accounts GUI |  |  |  | 3
|  | 12 | Periodic Reports for Accounts Report |  |  |  | 2
|  | 13 | Testing |  |  |  | 4
Task 18 | Members Dashboard | 1 | Letter Request - Draft GUI | [6 empty] | 3
|  | 2 | Letter Request - Database Design | [6 empty] | 1
|  | 3 | Letter Request - Middle Tier Logic | [6 empty] | 2
|  | 4 | Letter Request - Presentation Tier Logic | [6 empty] | 1
|  | 5 | Edit/ View Profile - Draft GUI | [6 empty] | 3
|  | 6 | Edit/ View Profile - Database Design | [6 empty] | 1
|  | 7 | Edit/ View Profile - Middle Tier Logic | [6 empty] | 2
|  | 8 | Edit/ View Profile - Presentation Tier Logic | [6 empty] | 1
|  | 9 | Membership Histroy - Draft GUI | [6 empty] | 3
|  | 10 | Membership Histroy - Database Design | [6 empty] | 1
|  | 11 | Membership Histroy - Middle Tier Logic | [6 empty] | 2
|  | 12 | Membership Histroy - Presentation Tier Logic | [6 empty] | 1
|  | 13 | Testing | [6 empty] | 4
Task 19 | System Log | 1 | System Log panal - Draft GUI | [9 empty] | 3
|  | 2 | Financial Transactions Section GUI - Draft GUI | [9 empty] | 2
|  | 3 | Detailed FInancial Transaction GUI - Draft GUI | [9 empty] | 3
|  | 4 | System Log panal - Database Design | [9 empty] | 1
|  | 5 | System Log panal - Middle Tier Logic | [9 empty] | 2
|  | 6 | System Log panal - Presentation Tier Logic | [9 empty] | 1
|  | 7 | Detailed Transaction Tier - Middle Tier Logic | [9 empty] | 2
|  | 8 | Detailed Transaction Screen - Presentation Tier Logic | [9 empty] | 1
|  | 9 | Testing | [9 empty] | 4
Task 20 | Acknowledgemt Mails | 1 | Acknowledgement Mails - Draft GUI | [9 empty] | 3
|  | 2 | Acknowledgement Mails - Database Design | [9 empty] | 1
|  | 3 | Acknowledgement Mails - Middle Tier Implementation | [9 empty] | 2
|  | 4 | Acknowledgement Mails - Presentation Tier Logic | [9 empty] | 1
|  | 5 | Testing | [9 empty] | 4
Task 21 | News Section Screen Edit (Admin) | 1 | News Section Screen GUI | 3
|  | 3 | Add/Edit News Items Presentation Tier Logic | 1
|  | 3 | Add/Edit News Items database design | 1
|  | 4 | Add/Edit News Items Middletier | 2
|  | 5 | Testing | 4
Task 22 | Executive Committee Management | 1 | Current ExCo Screen - Draft GUI | [6 empty] | 3
|  | 2 | Previous ExCos Screen - Draft GUI | [6 empty] | 3
|  | 3 | Detailed Exco Screen - Draft GUI | [6 empty] | 3
|  | 4 | Detailed Previous Exco Screen - Draft GUI | [6 empty] | 3
|  | 5 | ‌Add ExCo members and map user roles Screen - Draft GUI | [6 empty] | 3
|  | 6 | Add Exco Members - Presentation Tier Logic | [6 empty] | 1
|  | 7 | Add Exco Members - Middle Tier Logic | [6 empty] | 2
|  | 8 | Testing | [6 empty] | 4
Task 23 | Online Payment Gateway | 1 | Research for a suitable online payment gateway | 5
|  | 2 | Setup the payment gateway | 2
|  | 3 | Payment Page - Draft GUI | 3
|  | 4 | Payment Page - Database Design | 2
|  | 5 | Payment Page - Middle Tier Logic | 2
|  | 6 | Payment Page - Presentation Tier Logic | 1
|  | 7 | Testing | 5
Task 24 | Member Directory | 1 | Member Directory Draft GUI |  |  |  | 3
|  | 2 | Member Directory Middle Tier |  |  |  | 2
|  | 3 | Member Directory Presentation Tier |  |  |  | 2
|  | 4 | Member Detail View GUI |  |  |  | 3
|  | 5 | Member Detail View Middle Tier |  |  |  | 2
|  | 6 | Member Detail View Presentation Tier |  |  |  | 1
Task 25 | Preparation of Task Allocation | 1 | Planning the Task Allocation | 3 | 3 |  | 3 |  |  | 3 |  |  | 3
|  | 2 | Documenting the Task Breakdowns | 5 | 5 |  | 5 |  |  | 5 |  |  | 5
Task 26 | System Test | 1 | Full flow Testing | 4 |  |  | 1 |  |  | 1 |  |  | 2
|  | 2 | Bug Fixing | 4 |  |  | 1 |  |  | 1 |  |  | 2
Task 27 | Documentation | 1 | User Guide | 2 |  |  | 2 |  |  | 2 |  |  | 2
Total |  |  |  | 138 |  |  | 144.5 |  |  | 140.75 |  |  | 141.5